PRP

PRIVATE RUNTIME PLATFORM

# Delivery Roadmap

ลำดับงาน Dependencies และ Release Gates

PYTHON-FIRST  /  REUSE-BEFORE-BUILD

Phase 1 · Chat & Voice
Phase 2 · Generative Media

| Version / date | 0.3.0 / 20 September 2026 |
| --- | --- |
| Document status | Draft for review; framework selection pending G0 |
| Runtime evidence | NOT_RUN — no deployment or GPU qualification |
| Canonical source | docs/ROADMAP-PRP.md |

PRP ทำงานอิสระจาก Zuri กล่องในแบบแสดงหน้าที่ ไม่ได้สั่งให้เขียนทุกส่วนขึ้นใหม่ Framework reuse ต้องผ่านข้อกำหนดด้านสิทธิ์ ทรัพยากร และ recovery เดิม

# สารบัญหัวข้อ

1. Planning model

2. Milestones และ exit gates

3. Work breakdown และ dependencies

4. Parallel work และ critical path

5. Gate checklists

6. Team interfaces และ RACI

7. Risk burn-down และ decision triggers

8. Backlog policy และ definition of ready/done

9. Handoff package และ next execution order

10. Reuse-first gate refinement — v0.3.0

ฉบับนี้คงรหัสข้อกำหนดเดิม เพิ่ม NFR-019..024 และขั้นประเมิน A/B ก่อนเลือก runtime framework; โปรดดู Change Log ในชุดเอกสาร

เอกสารที่เกี่ยวข้อง: PRD · SRS · Tests · Operations

# 1. Planning model

Roadmap นี้เป็น dependency/gate-based plan ไม่ใช่คำมั่นกำหนดวันส่งมอบ เพราะยังไม่ทราบจำนวนผู้พัฒนาและ configuration จริง ไม่มี estimate จากจำนวน GB ของ GPU และไม่มีวันเริ่มผลิตที่สมมติขึ้น ผู้รับผิดชอบเป็น role ไม่ใช่การมอบหมายคนที่ยังไม่ยืนยัน

สถานะทุก work package เริ่ม NOT_STARTED เฉพาะ documentation package ชุดนี้เป็น DELIVERED_DRAFT ไม่ใช่ application implementation การอนุมัติ scope/model/license/quotas/SLO เป็น deliverable ของ G0/G2 ไม่ใช่สิ่งที่ทำเสร็จแล้ว

# 2. Milestones และ exit gates

| Milestone | Outcome | Entry | Exit evidence |
| --- | --- | --- | --- |
| G0 Design & qualification plan | independent platform baseline | request/old SRS reviewed | approved ownership, A/B fit-gap evidence (WP24), selected authority binding, API/state, threat model, inventory, candidate licenses |
| P1-A / G1 Chat foundation | keys + Router + two vLLM replicas + console | G0 frozen | clean install, compatible JSON/SSE, isolated principals, atomic admission/fault basics |
| P1-B / G2 Voice foundation | ASR/TTS + native jobs + artifact lifecycle | G1 core seams; speech spike may parallel | quality corpora, preset rights, headless worker, safe resident placement, client fallback |
| P1-C / G3 Core pilot | production-qualified core under approved load | G1/G2 evidence | W0-W4, restore/erasure/rollback, two-client isolation, operator signoff |
| LINE integration gate | selected OA adapter works safely | contracts + channel permission | separate authorized live canary; not needed to install/use core |
| P2-A Image | allowlisted image generation/edit | G3 + P2 SRS/quality freeze | media budgets/provenance/P1 regression + model qualification |
| P2-B Video | async video under measured envelope | image foundation + resource decision | actual duration/resolution/latency tests + chat reservation protection |

G1 ไม่เท่ากับจบ P1 ทั้งหมด G3 ไม่เท่ากับ LINE delivery ผ่านแล้ว ต้องรายงานสองสถานะแยกกัน Full-duplex, cloud provider fallback, customer-isolated multi-tenancy และ cluster HA เป็น future proposals ไม่แอบรวมไว้ P2

# 3. Work breakdown และ dependencies

## WP01 — Scope & ownership freeze

Stage: G0 | Owner: Product + Architecture | Depends on: None

ส่งมอบ: PRD/SRS boundaries, requirement IDs, job dimensions

Trace: G01/G02/G05 | Diagram D01,D03,D12 | สถานะ NOT_STARTED

## WP02 — Hardware & runtime discovery

Stage: G0 | Owner: Operations | Depends on: None

ส่งมอบ: GPU/CPU/RAM/OS/network inventory; model/license candidates

Trace: E02/E04 | Diagram D04,D18 | สถานะ NOT_STARTED

## WP24 — Runtime reuse fit-gap and A/B spikes

Stage: G0 | Owner: Architecture + Runtime + Security + QA | Depends on: WP01,WP02

ส่งมอบ: A-Xinference vs B-independent services evidence; conditional C-Ray; full requirement mapping; key-recovery gap; target-binding/retry/cancel tests; decision recommendation without fabricated benchmarks

Trace: NFR-020/023/024; FR-005/017/018/042 | Diagram D31,D33,D34 | สถานะ NOT_STARTED

## WP03 — Contracts & authority decision

Stage: G0 | Owner: API + Security | Depends on: WP01,WP24

ส่งมอบ: freeze public/management contracts, selected A/B binding, single key/admission authority, approved gaps and secret design

Trace: E01/E03/E05; NFR-020/023 | Diagram D08,D17,D31,D33 | สถานะ NOT_STARTED

## WP25 — Python engineering and environment baseline

Stage: P1-A | Owner: Build + Core + Operations | Depends on: WP03

ส่งมอบ: compatible pinned Python/toolchain and separate control/LLM/speech locks/images, typed ports, no-model-import tests and CI gates per Coding Standards

Trace: NFR-019/021/022 | Diagram D23,D30,D32 | สถานะ NOT_STARTED

## WP04 — Standalone control plane

Stage: P1-A | Owner: Core | Depends on: WP01,WP03,WP25

ส่งมอบ: thin Python control package, framework configuration/adapter seams, health and independent release; no duplicated vendor services

Trace: FR-001/002/050/054; NFR-019/021/022 | Diagram D02,D04,D32 | สถานะ NOT_STARTED

## WP05 — Identity/key/quota

Stage: P1-A | Owner: Identity | Depends on: WP03,WP04

ส่งมอบ: configure conforming key/RBAC authority and quota primitives; custom verifier/ledger only for approved gaps; object grants and revoke tests

Trace: FR-003..009/047 | Diagram D08,D17 | สถานะ NOT_STARTED

## WP06 — Registry/qualification

Stage: P1-A | Owner: Registry | Depends on: WP02,WP04

ส่งมอบ: reuse selected manager/service inventory with PRP profile/qualification mapping, actual resource identity and readiness receipts

Trace: FR-010..015/042 | Diagram D10,D14 | สถานะ NOT_STARTED

## WP07 — Router/admission/execution

Stage: P1-A | Owner: Router + Admission | Depends on: WP05,WP06

ส่งมอบ: configure/reuse router and admission primitives; implement only approved binding/atomicity/uncertainty gaps; test hidden retries and races

Trace: FR-016..022 | Diagram D09,D13 | สถานะ NOT_STARTED

## WP08 — Chat/stream contracts

Stage: P1-A | Owner: API + Chat Adapter | Depends on: WP03,WP07

ส่งมอบ: thin stable chat contract and selected runtime adapter, tokenizer budgets, JSON/SSE/tools-as-data; disable unaccounted retries

Trace: FR-023..028 | Diagram D06 | สถานะ NOT_STARTED

## WP09 — Text console & negative tests

Stage: P1-A | Owner: Console + QA | Depends on: WP05,WP08

ส่งมอบ: independent key/health UI; mock+DB races+isolation tests

Trace: FR-045/048/056 | Diagram D05,D21 | สถานะ NOT_STARTED

## WP10 — Speech extraction spike

Stage: P1-B | Owner: Speech | Depends on: WP02,WP03

ส่งมอบ: compare existing speech runtime with headless Lalin extraction; reuse engine pipeline, restrict routes, approve voice rights

Trace: FR-031/033/043 | Diagram D03,D18 | สถานะ NOT_STARTED

## WP11 — Artifacts/decode

Stage: P1-B | Owner: Artifact + Security | Depends on: WP05

ส่งมอบ: bounded upload, sandbox, checksums, ACL, TTL/erasure/share grants

Trace: FR-029/030/039..041 | Diagram D19,D20 | สถานะ NOT_STARTED

## WP12 — Native durable speech jobs

Stage: P1-B | Owner: Jobs | Depends on: WP07,WP11

ส่งมอบ: reuse durable job primitives or approved gap implementation; native ASR/TTS kinds, idempotency, state/cancel/recovery tests

Trace: FR-036..038 | Diagram D12 | สถานะ NOT_STARTED

## WP13 — ASR/TTS integration

Stage: P1-B | Owner: Speech + API | Depends on: WP10,WP11,WP12

ส่งมอบ: sync/async adapters, fidelity, no-speech and model manifest

Trace: FR-031..035/043 | Diagram D07 | สถานะ NOT_STARTED

## WP14 — Physical placement qualification

Stage: P1-B | Owner: Operations + QA | Depends on: WP06,WP13

ส่งมอบ: CPU speech or measured B headroom; resident budgets, no silent swaps

Trace: FR-018/044 | Diagram D04,D14 | สถานะ NOT_STARTED

## WP15 — Independent voice playground

Stage: P1-B | Owner: Client | Depends on: WP08,WP13

ส่งมอบ: record-send/upload, own voice-turn state, text fallback/TTS-only retry

Trace: FR-049 | Diagram D07 | สถานะ NOT_STARTED

## WP16 — Speech quality evidence

Stage: P1-B | Owner: QA + Product | Depends on: WP13

ส่งมอบ: fixed corpus/scorers, ASR CER/WER/entity and TTS listening evidence

Trace: NFR-008..010 | Diagram D25 | สถานะ NOT_STARTED

## WP17 — Mixed/fault/security qualification

Stage: P1-C | Owner: QA + Security | Depends on: WP09,WP14,WP15,WP16

ส่งมอบ: W0-W4, node/DB/observer failures, revoke/delete/uncertain execution

Trace: NFR/SEC | Diagram D13,D20,D25 | สถานะ NOT_STARTED

## WP18 — Operations and recovery

Stage: P1-C | Owner: Operations | Depends on: WP17

ส่งมอบ: alerts/runbooks, disaster restore, forward-safe rollback, release evidence

Trace: FR-046/051/052 | Diagram D21,D22,D23 | สถานะ NOT_STARTED

## WP19 — Portability & multi-app pilot

Stage: P1-C | Owner: API + QA | Depends on: WP18

ส่งมอบ: two clients, vendor-neutral replacement conformance, config export, pending-job/erasure preservation and key-rotation rehearsal

Trace: FR-053/054; NFR-024 | Diagram D26,D34 | สถานะ NOT_STARTED

## WP20 — External LINE adapter

Stage: LINE | Owner: Integration owner | Depends on: WP08,WP13

ส่งมอบ: signature/dedupe/content/ASR-chat-TTS/outbox/push/URL adapter

Trace: FR-055 | Diagram D11,D15 | สถานะ NOT_STARTED

## WP21 — Authorized LINE canary

Stage: LINE | Owner: Integration owner + QA | Depends on: WP20,WP17

ส่งมอบ: real channel permissions, quota, device playback, unknown-send recovery

Trace: INT-LINE gate | Diagram D11,D15 | สถานะ NOT_STARTED

## WP22 — Image contract & implementation

Stage: P2-A | Owner: Media + Security | Depends on: G3 complete + P2 scope freeze

ส่งมอบ: approved workflow/model, pixel/step quotas, async lineage

Trace: P2-001..008 | Diagram D24 | สถานะ NOT_STARTED

## WP23 — Video qualification & rollout

Stage: P2-B | Owner: Media + Operations | Depends on: WP22 + hardware evidence

ส่งมอบ: duration/resolution envelopes, reserved chat capacity, video safety/test

Trace: P2-001..008 | Diagram D24 | สถานะ NOT_STARTED

# 4. Parallel work และ critical path

Critical path: ownership/contracts -> access/registry -> admission/fencing -> chat -> speech jobs/placement/quality -> mixed load -> restore/rollback -> core pilot

ทำขนานได้: hardware/license discovery กับ API drafting; speech-runtime extraction กับ chat integration หลัง contract freeze; voice UI กับ artifact/worker contract mocks; LINE adapter development กับ core hardening โดยไม่ถือว่า mock/live result เท่ากัน

ห้ามทำขนานโดยไม่มี coordinator: เปลี่ยน SRS identity/state contracts, migrate shared schema, เปลี่ยน GPU resident budget และเปิด runtime ports; designated integrator ต้อง reconcile baseline แล้ว regenerate trace views เพียงรอบที่ควบคุมได้

# 5. Gate checklists

G0: ยืนยัน independent ownership, no Zuri dependency, one admission authority, P1 voice semantics, supported interfaces, error/state model, threat/retention assumptions, host inventory, stack choices
G1: real two-node qualification, wrong/missing auth refusal, physical ID dedupe, resource race, bounded queue, streaming interruption, no cloud egress, operator can revoke key
G2: approved ASR/TTS/preset manifests, corpus gates, upload/decode limits, async durable state, delete/late-result fencing, CPU/GPU resident placement, independent client voice cycle
G3: mixed chat protection, no admitted OOM, simulated host/coordinator failure, tested restore with erasure, release rollback, limited-content observability, two apps quota isolation, docs/config handoff
LINE: verified webhook/dedup, channel permission, ACK budget, reply token policy, push idempotency and quota, signed audio URL lifecycle, mobile/desktop playback

ไม่มี security waiver แบบเงียบ ๆ; scope/secret/uncertain resource/egress defect เป็น BLOCKED และห้ามรวมเป็น passed percentage หาก target performance ไม่ผ่าน ให้ปรับ profile/limits ด้วย change record และทดสอบใหม่ ไม่แก้เกณฑ์ย้อนหลังแล้วอ้างผลเก่าผ่าน

# 6. Team interfaces และ RACI

| Activity | Accountable | Responsible | Consulted |
| --- | --- | --- | --- |
| Product scope/targets | Product owner | Architect | QA/Operations |
| API/state/ownership | Technical owner | Core/API | Client/Integration |
| Keys/tenant/egress | Security owner | Identity/Core | Operations |
| Runtime/model/voice | Technical owner | Speech/LLM engineer | Product/license reviewer |
| Hardware qualification | Operations owner | QA + Runtime engineer | Admission engineer |
| Acceptance evidence | QA owner | Test maintainers | Security/Product |
| Production/rollback | Release owner | Operator | QA/Integration |
| LINE channel rollout | Integration owner | LINE adapter maintainer | Channel owner |

ทีมเล็กอาจเป็นคนเดียวหลาย role แต่ผู้อนุมัติและผู้ลงมือในหลักฐานต้องระบุจริงก่อน rollout ไม่มีการตั้งชื่อบุคคลหรือให้สิทธิ์ production ในเอกสารนี้

# 7. Risk burn-down และ decision triggers

| Risk | First proof | Stop / decision trigger |
| --- | --- | --- |
| Model does not fit alongside speech | WP02/WP14 measured profile | เปลี่ยน model/context/CPU placement หรือประกาศ reduced chat replica; ห้าม silent swap |
| Voice quality below target | WP10/WP16 corpus | เปลี่ยน preset/engine; G2 blocked |
| Gateway/native scheduler conflict | WP03/WP07 race test | เลือก single authority chain ก่อน implementation |
| Storage/tombstone mismatch | WP11/WP18 restore test | หยุด artifact reads จน reconcile |
| Hidden desktop dependency | WP10 clean headless package | extract adapter/service profile แทนยกทั้ง Studio |
| LINE account access unavailable | WP20 contract tests | core G3 ยังประเมินได้ แต่ LINE gate BLOCKED |
| Two hosts share outage domain | WP18 failure drill | disclose SPOF; เพิ่ม HA เป็น requirement ใหม่หากจำเป็น |

# 8. Backlog policy และ definition of ready/done

Ready: linked requirement IDs, owner, dependency status, approved acceptance, data/privacy impact, API/schema diff, rollback approach และ test level
Done: implementation exists, exact commit/image/profile identified, applicable test evidence PASS, docs/trace updated, deployment reversible และไม่มี unresolved critical issue

Documentation-only task done ไม่เปลี่ยน runtime test เป็น PASS Contract stub ไม่เป็น implementation completion Endpoint screenshot ไม่พิสูจน์ concurrency หรือ safe restart

# 9. Handoff package และ next execution order

Integrator เริ่ม WP01/WP02 -> WP24 -> WP03 ก่อน แล้ว WP25 -> WP04 ไม่สร้าง repository หรือส่ง credential จริงจากไฟล์นี้ เปิด implementation issue ต่อ work package โดย link PRP IDs และ evidence placeholder ใช้ branch/PR ตาม workflow ของ repository PRP ที่เลือก ไม่ยืม registry หรือ requirement number ของ Zuri

Deliverables ก่อน core pilot: pinned deployment manifests, model/voice rights receipts, executable contract tests, benchmark fixtures/results, admin/bootstrap/key/runbook, backup/restore receipts, API schema export และ known-limitations sheet

# 10. Reuse-first gate refinement — v0.3.0

G0 ไม่ผ่านเพียงเพราะมี diagram: ต้องมี WP24 fit-gap ครบ 92 P1 requirements, source/experiment evidence แยกกัน, actual target/epoch binding, key-verifier conformance, cancellation และ framework retry policy ก่อน WP03 เลือก stack

WP25 สร้าง engineering baseline หลัง stack contract ตกลงแล้วและก่อน WP04 production code; isolated throwaway spike ใน WP24 อนุญาตก่อนหน้าได้ ไม่อ้างเป็น production implementation

เส้นทางหลักที่เพิ่ม: WP01/WP02 -> WP24 -> WP03 -> WP25 -> WP04 -> WP05/WP06 -> WP07 -> WP08/WP09 จากนั้น voice และ qualification ตามเดิม WP20 ทำขนานกับ WP17 ได้หลัง WP08/WP13; WP21 ยังรอ core qualification และ authorization

Work package ชื่อ Identity/Registry/Router/Jobs หมายถึงส่งมอบ capability ไม่ใช่สั่งเขียน service ใหม่โดยอัตโนมัติ issue implementation ต้องระบุ disposition REUSE/CONFIGURE/ADAPT/BUILD-GAP พร้อม requirement/evidence และขอบเขตการทดสอบ

เมื่อ A/B ไม่ผ่าน ให้บันทึก BLOCKED พร้อม gap แล้วตัดสินใจ reduce scope/เปลี่ยน candidate/อนุมัติ gap code ด้วย change control ไม่เพิ่ม framework อีกตัวโดยไม่มี owner แผนไม่มีวันเสร็จที่สมมติและไม่เปลี่ยนการมีสองเครื่องเป็น HA

# ภาพอ้างอิงและเอกสารประกอบ

## D27 — Roadmap dependencies and parallel lanes

ลำดับตาม gate ไม่สมมติวันเสร็จ; LINE acceptance แยกจาก core pilot

Full vector / editable source: PRP-Diagram-Atlas.html และ diagrams/source ใน ZIP

## D31 — Reuse-first framework evaluation

เปรียบเทียบ A/B ก่อนเลือก stack; source review ไม่เท่ากับ runtime PASS และ critical gap ห้ามถูกคะแนนรวมกลบ

Full vector / editable source: PRP-Diagram-Atlas.html และ diagrams/source ใน ZIP